## BURNDOWN CHART
BURNDOWN CHART
Days | Goal velocity | Actual
0 | 24 | 24
1 | 22.8 | 24
2 | 21.6 | 20
3 | 20.4 | 20
4 | 19.2 | 20
5 | 18 | 18
6 | 16.8 | 16
7 | 15.6 | 16
8 | 14.4 | 16
9 | 13.2 | 12
10 | 12 | 12
11 | 10.8 | 12
12 | 9.6 | 10
13 | 8.4 | 8
14 | 7.2 | 8
15 | 6 | 8
16 | 4.8 | 5
17 | 3.6 | 0
18 | 2.4 | 0
19 | 1.2 | 0
20 | 0 | 0

## PROJECT DETAILS (hidden)
PROJECT NUMBER
PROJECT NAME
PROJECT MANAGER
DATE
VERSION

## INSTRUCTIONS (hidden)
Instructions
Days
Change this to the timescale that you want to appear at the bottom of the chart (the x axis).
Goal or target
Enter the number of features/story points that you plan to achieve in each time period. This forms the yellow line showing goal velocity on the chart.
Done or actual
Record how many features/story points that you actually achieve.
Goal or target velocity
This is a calculated field that counts down the target points to zero (completion of the project). It forms the left side of the chart (the y axis).
Remaining
This is a calculated field that simply deducts Done from Remaining. It is the blue line showing the actual burndown rate on the chart.

## RESOURCES (hidden)
Useful resources
Project Management Templates
The Top 50 Business Risks (and how to manage them)!
Issue Log Template [free download]
End Project Report Template
Risk Register Template
Stakeholder Management Templates
Work Breakdown Structure (WBS) template in Excel